## WF Gantt chart
Developer | 27-Jul | 28-Jul | 29-Jul | 30-Jul | 31-Jul | 01-Aug | 02-Aug | 03-Aug | 04-Aug | 05-Aug | 06-Aug | 07-Aug | 08-Aug | 09-Aug | 10-Aug | 11-Aug | 12-Aug | 13-Aug | 14-Aug | 15-Aug | 16-Aug | 17-Aug | 18-Aug | 19-Aug | 20-Aug | 21-Aug
Amey Surve |  |  |  | Video Listing [FNS-76] - 1h Photo Listing [FNS-74] - 1h News Listing [FNS-72] - 1h | Video Listing [FNS-76] - 2h 30m Photo Listing [FNS-74] - 1h 30m News Detail [FNS-73] - 1h News Listing [FNS-72] - 1h 30m |  |  | Media Listing [FNS-80] - 3h Video Detail [FNS-77] - 2h Photo Detail [FNS-75] - 2h News Detail [FNS-73] - 1h | Video Detail [FNS-77] - 2h Photo Listing [FNS-74] - 1h 30m News Detail [FNS-73] - 2h News Listing [FNS-72] - 1h 30m | Media Listing [FNS-80] - 2h Community Detail [FNS-79] - 30m Community Listing [FNS-78] - 30m Photo Detail [FNS-75] - 3h | Terms & Conditions [FNS-83] - 4h About [FNS-81] - 4h | Video Redirect Bug [FNS-128] - 10m Video Title Font Size [FNS-125] - 5m Photo Cards Clickable [FNS-123] - 5m Swiper Nav Alignment [FNS-121] - 1h Widget Titles Caps [FNS-120] - 10m | [12 empty] | QA sanity fixes [FNS-210] - 8h
Ayush Shah | Homepage Header & Footer [FNS-61] - 6h | Homepage Header & Footer [FNS-61] - 6h | Homepage Static Banner [FNS-63] - 2h Homepage Header & Footer [FNS-61] - 4h | Homepage Schedule Widget [FNS-64] - 6h | Homepage Schedule Widget [FNS-64] - 6h |  |  | Buy Tickets URL JSON [FNS-88] - 2h Fixtures & Results [FNS-87] - 4h | Matchcentre [FNS-93] - 6h | Matchcentre [FNS-93] - 6h | Matchcentre [FNS-93] - 6h | Matchcentre [FNS-93] - 6h |  |  | Matchcentre [FNS-93] - 6h
Mayur Kale | [7 empty] | Standing UI development [FNS-92] - 3h Standings API integration [FNS-91] - 3h Homepage Standings widget [FNS-65] - 2h | Standing UI development [FNS-92] - 3h Standings API integration [FNS-91] - 3h Homepage Standings widget [FNS-65] - 2h | Stats UI [FNS-90] - 4h Stats API integration [FNS-89] - 4h | Stats UI [FNS-90] - 4h Stats API integration [FNS-89] - 4h
Shubham Sawant | Homepage Showcase Carousel [FNS-62] - 4h Homepage News & Videos [FNS-66] - 4h | Homepage Photos [FNS-67] - 3h Homepage Squad [FNS-68] - 4h | Homepage Shop Widget [FNS-69] - 2h Homepage Newsletter Widget [FNS-70] - 6h | Squad Page [FNS-94] - 8h | 404 [FNS-84] - 1h Custom JSON [FNS-96] - 7h |  |  | Custom JSON [FNS-96] - 2h Player Profile [FNS-95] - 6h | Player Profile [FNS-95] - 10h
total
Run |  |  |  | 3 | 6.5 |  |  | 8 | 7 | 6 | 8 | 1.5 |  |  |  | 48
Build | 14 | 13 | 14 | 14 | 14 |  |  | 22 | 24 | 14 | 14 | 6 |  |  | 6 | 155
203
Shubham | 61
Ayush | 64
Amey | 48
Mayur | 32
46

## WF Tracker
Pages | Status | Link | Developer | Development Deadline
Migration | Development completed |  | Rinston | 2026-08-04
HP - Top menu, Bottom Menu/Footer, Static Banner, Fixtures, | Development completed | Link | Ayush | 2026-08-04
HP - News ,Photos , Videos ,Squad ,shop ,Showcase,Newsletter | Development completed |  | Shubham | 2026-08-04
HP - Standings | Development completed |  | Mayur | 2026-08-04
News - Listing & Detail | Development completed | Link | Amey | 2026-08-04
Videos - Listing & Detail | Development completed | Link | Amey | 2026-08-04
Photos - Listing & Detail | Development completed | Link | Amey | 2026-08-04
Media - Press Releases (Link out to external news) | Development completed | Link | Amey | 2026-08-04
Fixtures & Results | Development completed | Link | Ayush | 2026-08-04
Squad | Development completed | Link | Shubham | 2026-08-04
Standings | Development completed | Link | Mayur | 2026-08-04
Phase 2
JSON feed for Buy tickets for fixtures | Development completed | N.A | Ayush | 2026-08-12
Community - Same as news listing & detail | Development completed |  | Amey | 2026-08-07
About | Development completed | Link | Amey | 2026-08-07
Privacy Policy | Development completed |  | Amey | 2026-08-07
Terms & Conditions | Development completed | Link | Amey | 2026-08-07
Sign up Form | Development completed | Link | Shubham | 2026-08-07
Page Not Found. (404) | Development completed |  | Shubham | 2026-08-07
Stats | Development completed |  | Mayur | 2026-08-07
Matchcentre | Development completed | Link | Ayush | 2026-08-07
GTM | Development completed |  | Ayush | 2026-08-07
Sitemap | Development completed |  | Ayush | 2026-08-07
Robots | Development completed |  | Ayush | 2026-08-07
Player Profile | Development completed | Link | Shubham | 2026-08-12
Custom JSON feed for Player Profile & squad | Development completed | N.A | Shubham | 2026-08-12

## SO gantt chart
Developer | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21
Amey | Home - News [FNS-10] — 4h Home - Videos [FNS-101] — 4h | Points Table [FNS-51] — 5h Stats [FNS-49] — 2h Showcase [FNS-6] — 1.5h | Home - shop [FNS-13] — 8h | Schedule [FNS-41] — 2h Home - Fixtures [FNS-8] — 6h | Header & Footer, Sponsors [FNS-5] — 8h |  |  | Home - Players [FNS-12] — 8h | Home - Players [FNS-12] — 4h | FREE Due Blocker | Wf fixses | Home - Players [FNS-12] - 1h Schedule [FNS-41] — 2h Players [FNS-44] — 3h |  |  | Players [FNS-44] — 8h | Schedule [FNS-41] — 8h | Schedule [FNS-41] — 2h Support Staff [FNS-45] — 6h | player Profile [FNS-46] — 7.30h | FREE |  |  | FREE | FREE | FREE | FREE | FREE |  |  | FREE | FREE | FREE | FREE | FREE
Mala | Na | Na | Na | Na | Na |  |  | Na | Na | Na | Na | Leave |  |  | Leave | Terms and Conditions [FNS-29] — 4h Privacy Policy [FNS-28] — 4h | Thank you [FNS-31] — 4h 404 [FNS-30] — 4h | Partnership Framework [FNS-32] — 4h Where to Watch [FNS-24] — 4h | Womens t20 exhibition [FNS-25] — 4h Wallpapers [FNS-23] — 4h |  |  | Wallpapers [FNS-23] — 4h | FREE | FREE | FREE | FREE |  |  | FREE | FREE | FREE | FREE | FREE
Siddharth N | Na | Na | Na | Na | Na |  |  | Na | Na | Na | Na | Na |  |  | Registration form (popup) [FNS-33] — 4h — [FNS-34] — 4h | Contact Us [FNS-35] — 4h — [FNS-36] — 4h | Boundary Builder page + form [FNS-168] — 8h | Unit testing fixses of all form -8h | FREE |  |  | FREE | FREE | FREE | FREE | FREE |  |  | FREE | FREE | FREE | FREE | FREE
Supriya | Na | Na | Na | Na | Na |  |  | Videos - Listing [FNS-20] — 4h Photos - Listing [FNS-18] — 4h | News - Listing [FNS-16] — 8h | Photos - Listing [FNS-18] — 2h Photos - Detail [FNS-19] — 6h | News - Detail [FNS-17] — 4h Fixses - 4h | Leave |  |  | Videos - Detail [FNS-21] — 5h Showcase -3h | Matchcentre [FNS-43] — 8h | Matchcentre [FNS-43] — 8h | Matchcentre [FNS-43] — 8h | FREE |  |  | FREE | FREE | FREE | FREE | FREE |  |  | FREE | FREE | FREE | FREE | FREE
Ayush | Na | Na | Na | Na | Na |  |  | Na | Na | Na | Na | Na |  |  | Na | Na | Na | Na | Na |  |  | FREE | FREE | FREE | FREE | FREE |  |  | FREE | FREE | FREE | FREE | FREE

## SO Tracker
Page type | Page | URLs | Tickets | Assignee | Status | Est Hours | Comments | Start date | Development Deadline | Website Go-Live
Global | Header & Footer, Sponsors | https://www.seattleorcas.com/ | https://sportzinteractive.atlassian.net/browse/FNS-5 | Amey | Hold | 8 |  |  | 2026-08-21 | 3rd Sep 2026
Homepage | Home - showcase | https://www.seattleorcas.com/ | https://sportzinteractive.atlassian.net/browse/FNS-6 | Supriya | In progress | 4 |  | 2026-08-25 | 2026-08-25
| Home - Fixtures | https://www.seattleorcas.com/ | https://sportzinteractive.atlassian.net/browse/FNS-8 | Amey | In progress | 6 | unit testing remaining with cricketapi |  | 2026-08-21
| Home - shop | https://www.seattleorcas.com/ | https://sportzinteractive.atlassian.net/browse/FNS-13 | Amey | Testing | 8 |  |  | 2026-08-20
| Home - international & Domestic Players (Hidden ) | https://www.seattleorcas.com/ | https://sportzinteractive.atlassian.net/browse/FNS-7 |  | Yet to start |  | No need to create this section |  | NA
| Home - Players | https://www.seattleorcas.com/ | https://sportzinteractive.atlassian.net/browse/FNS-12 | Amey | In progress | 12 |  |  | 2026-08-21
| Home - News | https://www.seattleorcas.com/ | https://sportzinteractive.atlassian.net/browse/FNS-10 | Amey | Testing | 4 |  |  | 2026-08-20
| Home - Videos | https://www.seattleorcas.com/ | https://sportzinteractive.atlassian.net/browse/FNS-101 | Amey | Testing | 4 |  |  | 2026-08-20
| Home - Photos (Hidden) | https://www.seattleorcas.com/ | https://sportzinteractive.atlassian.net/browse/FNS-11 | Supriya | Hold
| Home - Social Wall | https://www.seattleorcas.com/ | https://sportzinteractive.atlassian.net/browse/FNS-14 | Amey | Yet to start |  |  |  | 2026-08-26
Content | News - Listing | https://www.seattleorcas.com/news | https://sportzinteractive.atlassian.net/browse/FNS-16 | Supriya | Development completed | 8 |  | 2026-08-24 | 2026-08-24
| News - Detail | https://www.seattleorcas.com/news/seattle-orcas-launch-inaugural-womens-t20-exhibition-for-2026 | https://sportzinteractive.atlassian.net/browse/FNS-17 | Supriya | In progress | 4 |  | 2026-08-14 | 2026-08-14
| Photos - Listing | https://www.seattleorcas.com/photos | https://sportzinteractive.atlassian.net/browse/FNS-18 | Supriya | Development completed | 6 |  |  | 2026-08-24
| Photos - Detail | https://www.seattleorcas.com/photos/texas-super-kings-vs-seattle-orcas-best-snaps-from-the | https://sportzinteractive.atlassian.net/browse/FNS-19 | Supriya | In progress | 6 |  |  | 2026-08-24 |  | 2026-08-10
| Videos - Listing | https://www.seattleorcas.com/videos | https://sportzinteractive.atlassian.net/browse/FNS-20 | Supriya | Development completed | 4 |  |  | 2026-08-24
| Videos - Detail | https://www.seattleorcas.com/videos/seattle-orcas-are-back-major-league-season-3 | https://sportzinteractive.atlassian.net/browse/FNS-21 | Supriya | In progress | 4 |  |  | 2026-08-24
Data | Schedule | https://www.seattleorcas.com/schedule | https://sportzinteractive.atlassian.net/browse/FNS-41 | Amey | In progress | 4 |  |  | 2026-08-21
| Points Table | https://www.seattleorcas.com/points-table | https://sportzinteractive.atlassian.net/browse/FNS-51 | Amey | Hold | 4 | resuable filter to be developed by build , rest UI done |  | 2026-08-20
|  |  | https://sportzinteractive.atlassian.net/browse/FNS-50 | Amey | Hold |  |  |  | 2026-08-20
| Stats | https://www.seattleorcas.com/stats | https://sportzinteractive.atlassian.net/browse/FNS-49 | Amey | Hold | 4 | resuable filter to be developed by build , rest UI done |  | 2026-08-20
|  |  | https://sportzinteractive.atlassian.net/browse/FNS-48 | Amey | Hold |  |  |  | 2026-08-20
| Matchcentre | https://www.seattleorcas.com/schedule/seattle-orcas-vs-san-francisco-unicorns-seosfu07112026270182 | https://sportzinteractive.atlassian.net/browse/FNS-43 | Supriya | In progress | 24 |  |  | 2026-09-11
| Players | https://www.seattleorcas.com/players | https://sportzinteractive.atlassian.net/browse/FNS-44 | Amey | In progress | 16 |  |  | 2026-08-28
| player Profile | https://www.seattleorcas.com/players/matthew-breetzke-65618-profile | https://sportzinteractive.atlassian.net/browse/FNS-46 | Amey | Yet to start | 16 |  |  | 2026-09-04
| Support Staff | https://www.seattleorcas.com/support-staff | https://sportzinteractive.atlassian.net/browse/FNS-45 | Amey | Yet to start | 8 |  |  | 2026-09-02
| Custom JSON |  | https://sportzinteractive.atlassian.net/browse/FNS-47 | Shubham | Yet to start
Forms | Registration form (popup) | https://www.seattleorcas.com/registration | https://sportzinteractive.atlassian.net/browse/FNS-33 | Siddharth N | Testing | 4 |  | 2026-08-24 | 2026-08-26
|  |  | https://sportzinteractive.atlassian.net/browse/FNS-34 | Siddharth N | Hold | 4 | Need country api
| Contact Us | https://www.seattleorcas.com/contact-us | https://sportzinteractive.atlassian.net/browse/FNS-35 | Siddharth N | In progress | 4 |  | 2026-08-25 | 2026-08-26
|  |  | https://sportzinteractive.atlassian.net/browse/FNS-36 | Siddharth N | Hold | 4 | Need country api
| Boundary Builder page + form | https://www.seattleorcas.com/boundary-builder | https://sportzinteractive.atlassian.net/browse/FNS-168 | Siddharth N | Yet to start | 8 |  | 2026-08-27 | 2026-08-27
|  |  | https://sportzinteractive.atlassian.net/browse/FNS-40 | Siddharth N | Yet to start | 8
| Volunteers (Not Live) | https://stg.seattleorcas.com/volunteers | https://sportzinteractive.atlassian.net/browse/FNS-37 |  | Yet to start |  | No need to create this page |  | NA
|  |  | https://sportzinteractive.atlassian.net/browse/FNS-38 |  | Yet to start |  | No need to create this page |  | NA
Static Pages | Wallpapers | https://www.seattleorcas.com/podsquad/wallpapers | https://sportzinteractive.atlassian.net/browse/FNS-23 | Mala | Yet to start | 8 |  | 2026-08-26 | 2026-08-26
| Where to Watch | https://www.seattleorcas.com/podsquad/where-to-watch | https://sportzinteractive.atlassian.net/browse/FNS-24 | Mala | Yet to start | 4 |  | 2026-08-27 | 2026-08-27
| Thank you | https://www.seattleorcas.com/thank-you | https://sportzinteractive.atlassian.net/browse/FNS-31 | Mala | Testing | 4 |  | 2026-08-25 | 2026-08-25
| Partnership Framework | https://www.seattleorcas.com/partnership-framework | https://sportzinteractive.atlassian.net/browse/FNS-32 | Mala | Testing | 4 |  | 2026-08-25 | 2026-08-25
| Womens t20 exhibition | https://www.seattleorcas.com/womens-t20-exhibition | https://sportzinteractive.atlassian.net/browse/FNS-25 | Mala | Yet to start | 4
| Terms and Conditions | https://www.seattleorcas.com/terms-and-conditions | https://sportzinteractive.atlassian.net/browse/FNS-29 | Mala | Testing | 4 |  | 2026-08-20 | 2026-08-25
| Privacy Policy | https://www.seattleorcas.com/privacy-policy | https://sportzinteractive.atlassian.net/browse/FNS-28 | Mala | Testing | 4 |  | 2026-08-20 | 2026-08-25
| 404 | https://www.seattleorcas.com/404 | https://sportzinteractive.atlassian.net/browse/FNS-30 | Mala | Testing | 4 |  | 2026-08-25 | 2026-08-25
222

## PVL gantt chart
Developer | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19
Amey | Na | Na | Na | Na | Na |  |  | Header & Footer - 8h | Standings - 6h | Squad - 8h | Squad - 4h External links - 1 ticket maybe | Testing |  |  | Na | Na | Na | Na | Na
Mala | Player registration embed - 1h HP Static Banner - 0.5h Team strip - 2h 404 - 0.5h | T&C page - 4h About us - 3h | Hall of fame - 6h | Testing | Free |  |  | Na | Na | Na | Na | Na |  |  | Na | Na | Na | Na | Na
Supriya | Homepage listings - 5h | All listing pages - 8h | All Detail pages - 8h | All Detail pages - 4h HP Showcase - 2h | Buffer Due to FIH |  |  | Na | Na | Na | Na | Na |  |  | Na | Na | Na | Na | Na

## PVL Tracker
Page type | Page | URLs | Tickets | Assignee | Status | Est Hours | Comments | Start Date | End Date
Global | Header & Footer, Sponsors | https://www.primevolleyballleague.com/ |  | Amey | Yet to start | 8 |  | 2026-09-07 | 2026-09-07
Homepage | Home - showcase | https://www.primevolleyballleague.com/ |  | Supriya | Yet to start | 2 |  | 2026-08-31 | 2026-08-31
| Static Banner + Team Strip | https://www.primevolleyballleague.com/ |  | Mala | Yet to start | 0.5 |  | 2026-08-31 | 2026-08-31
| Home - Standings | https://www.primevolleyballleague.com/ |  | Amey | Yet to start | 6 |  | 2026-09-08 | 2026-09-08
| Home - All Listing | https://www.primevolleyballleague.com/ |  | Supriya | Yet to start | 5 |  | 2026-08-31 | 2026-08-31
Content | All Listing pages | https://www.primevolleyballleague.com/news |  |  | Yet to start | 8 |  | 2026-09-01 | 2026-09-01
| All Detail page | https://www.primevolleyballleague.com/news/pvl-2025-bengaluru-torpeodes-book-a-date-with-mumbai-meteors-in-the-final |  |  | Yet to start | 8 |  | 2026-09-02 | 2026-09-02
| Photo Detail page | https://www.primevolleyballleague.com/blogs |  |  | Yet to start | 4 |  | 2026-09-03 | 2026-09-03
Static Pages | T&C page + About us |  |  | Mala |  | 4 + 3 |  | 2026-09-01 | 2026-09-01
| Hall of fame |  |  | Mala |  | 6 |  | 2026-09-02 | 2026-09-02
Data Pages | Squads (one regex page for every team) | https://www.primevolleyballleague.com/squads/ahmedabad-defenders-69 |  | Amey | Yet to start | 12 |  | 2026-09-09 | 2026-09-10

## MCFC Tracker
Page type | Page | URL | Tickets | Assignee | Status | Est Hours | Comments | Start Date | End Date
Homepage | Top Menu, Bottom Menu/Footer |  |  | Amey |  | 12 |  | 2026-09-14 | 2026-09-15
Homepage | Showcase |  |  | Shubham |  | 8 |  | 2026-09-16 | 2026-09-16
Homepage | Fixtures |  |  | Shubham |  | 20 | New molecule
Homepage | Standings |  |  | Amey |  | 6 |  | 2026-09-17 | 2026-09-17
Homepage | Buy Tickets banner -0.5 |  |  | Mala
Homepage | News |  |  | Amey |  | 4 |  | 2026-09-18 | 2026-09-18
Homepage | Subscribe to emails form |  |  | Siddharth N |  | 5 |  | 2026-09-21 | 2026-09-21
Homepage | Islander Banner -0.5 |  |  | Mala
Homepage | Videos |  |  | Amey |  | 4 |  | 2026-09-21 | 2026-09-22
Homepage | Aapla 12th Man Banner |  |  | Siddharth N |  | 8
Homepage | Squad |  |  | Shubham |  | 8 |  | 2026-09-23 | 2026-09-23
Homepage | Photos |  |  | Amey |  | 2 |  | 2026-09-24 | 2026-09-25
Homepage | Tracker |  |  | Ayush |  | 16 |  | 2026-09-10 | 2026-09-11
Homepage | Social Hub - 6 |  |  | Mala
Content | News Listing & Detail |  |  | Amey |  | 4 |  | 2026-09-25 | 2026-09-28
Content | Video Listing and Detail |  |  | Amey |  | 4 |  | 2026-09-29 | 2026-09-30
Content | Photos Listing & Detail |  |  | Amey |  | 8 |  | 2026-10-01 | 2026-10-02
Login | Login |  |  | Ayush |  | 12
Profile | Profile |  |  | Ayush |  | 24
Data | Squad |  |  | Shubham |  | 8
Data | Player Profile |  |  | Ayush |  | 20 |  | 2026-09-08 | 2026-09-10
Data | Standings |  |  | Amey |  | 4
Data | Fixtures |  |  | Shubham |  | 12
Data | Matchcentre |  |  | Ayush |  | 56 |  | 2026-08-31 | 2026-09-07
Other | Esports -4 |  |  | Mala
Other | Esports Player Profile -4 |  |  | Mala
Static Pages | Terms & Conditions -2 |  |  | Mala
Static Pages | Ticket T&C -2 |  |  | Mala
Static Pages | Community -2 |  |  | Mala
Static Pages | Safeguarding -4 |  |  | Mala
Static Pages | Privacy Policy -2 |  |  | Mala
Static Pages | Cookie Policy -2 |  |  | Mala
Static Pages | Error Page -4 |  |  | Mala
Poll | New Crest |  |  | Siddharth N |  | 40
Poll | New Crest Contest Terms and Conditions |  |  | Siddharth N
Poll | Islander of the match |  |  | Siddharth N
Poll | Goal of the Month |  |  | Siddharth N
Poll | Goal of the season |  |  | Siddharth N
Poll | Aapla 12th Man Poll |  |  | Siddharth N
Poll | Islander of the month |  |  | Siddharth N
Poll | Save of the Month |  |  | Siddharth N
Poll | Save of the Season |  |  | Siddharth N
Shop | Shop

## MCFC gantt chart
Developer | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13
Amey | bar: 2026-09-14 to 2026-09-18; 2026-09-21 to 2026-09-25; 2026-09-28 to 2026-10-02
Mala | bar: 2026-09-14 to 2026-09-18; 2026-09-21 to 2026-09-25; 2026-09-28 to 2026-10-02
Shubham | bar: 2026-09-14 to 2026-09-18; 2026-09-21 to 2026-09-25; 2026-09-28 to 2026-10-02
Ayush | bar: 2026-09-14 to 2026-09-18; 2026-09-21 to 2026-09-25; 2026-09-28 to 2026-10-02

## Combined
Developer | 27-Jul | 28-Jul | 29-Jul | 30-Jul | 31-Jul | 01-Aug | 02-Aug | 03-Aug | 04-Aug | 05-Aug | 06-Aug | 07-Aug | 08-Aug | 09-Aug | 10-Aug | 11-Aug | 12-Aug | 13-Aug | 14-Aug | 15-Aug | 16-Aug | 17-Aug | 18-Aug | 19-Aug | 20-Aug | 21-Aug | 22-Aug | 23-Aug | 24-Aug | 25-Aug | 26-Aug | 27-Aug | 28-Aug | 29-Aug | 30-Aug | 31-Aug | 01-Sep | 02-Sep | 03-Sep | 04-Sep | 05-Sep | 06-Sep | 07-Sep | 08-Sep | 09-Sep | 10-Sep | 11-Sep | 12-Sep | 13-Sep | 14-Sep | 15-Sep | 16-Sep | 17-Sep | 18-Sep | 19-Sep | 20-Sep | 21-Sep | 22-Sep | 23-Sep | 24-Sep | 25-Sep | 26-Sep | 27-Sep | 28-Sep | 29-Sep | 30-Sep | 01-Oct | 02-Oct | 03-Oct | 04-Oct | 05-Oct | 06-Oct | 07-Oct | 08-Oct | 09-Oct | 10-Oct | 11-Oct | 12-Oct | 13-Oct | 14-Oct | 15-Oct | 16-Oct | 17-Oct | 18-Oct | 19-Oct | 20-Oct | 21-Oct | 22-Oct | 23-Oct | 24-Oct | 25-Oct | 26-Oct | 27-Oct | 28-Oct | 29-Oct | 30-Oct
Amey | NA | NA | NA | WF- Video Listing [FNS-76] - 1h Photo Listing [FNS-74] - 1h News Listing [FNS-72] - 1h | WF- Video Listing [FNS-76] - 2h 30m Photo Listing [FNS-74] - 1h 30m News Detail [FNS-73] - 1h News Listing [FNS-72] - 1h 30m |  |  | WF- Media Listing [FNS-80] - 3h Video Detail [FNS-77] - 2h Photo Detail [FNS-75] - 2h News Detail [FNS-73] - 1h | WF- Video Detail [FNS-77] - 2h Photo Listing [FNS-74] - 1h 30m News Detail [FNS-73] - 2h News Listing [FNS-72] - 1h 30m | WF- Media Listing [FNS-80] - 2h Community Detail [FNS-79] - 30m Community Listing [FNS-78] - 30m Photo Detail [FNS-75] - 3h | WF- Terms & Conditions [FNS-83] - 4h About [FNS-81] - 4h | WF- Video Redirect Bug [FNS-128] - 10m Video Title Font Size [FNS-125] - 5m Photo Cards Clickable [FNS-123] - 5m Swiper Nav Alignment [FNS-121] - 1h Widget Titles Caps [FNS-120] - 10m |  |  | SO- Home - News [FNS-10] — 4h Home - Videos [FNS-101] — 4h | SO- Points Table [FNS-51] — 5h Stats [FNS-49] — 2h Showcase [FNS-6] — 1.5h | SO- Home - shop [FNS-13] — 8h | SO- Schedule [FNS-41] — 2h Home - Fixtures [FNS-8] — 6h | SO- Header & Footer, Sponsors [FNS-5] — 8h |  |  | SO- Home - Players [FNS-12] — 8h | SO- Home - Players [FNS-12] — 4h | SO- FREE Due Blocker | WF- QA sanity fixes [FNS-210] - 8h WF GO Live SO- Wf fixses | SO- Home - Players [FNS-12] - 1h Schedule [FNS-41] — 2h Players [FNS-44] — 3h |  |  | SO- Players [FNS-44] — 8h | SO- Schedule [FNS-41] — 8h | SO- Schedule [FNS-41] — 2h Support Staff [FNS-45] — 6h | SO- player Profile [FNS-46] — 7.30h | Holiday |  |  | SO- Fixses | SO- Fixses | SO- Fixses | SO- Support | SO- GO Live |  |  | Top Menu, Bottom Menu -6 Footer -2 | Both Standings css - 8 | HP News - 3 HP Videos - 3 HP Photos - 2 | News Listing & Detail Video Listing and Detail | Photos Listing & Detail |  |  | Holiday | Leave | Leave | Leave | Leave |  |  | MCFC Fixses | MCFC Fixses | MCFC Fixses | MCFC Fixses | Go Live
Ayush | WF- Homepage Header & Footer [FNS-61] - 6h | WF- Homepage Header & Footer [FNS-61] - 6h | WF- Homepage Static Banner [FNS-63] - 2h Homepage Header & Footer [FNS-61] - 4h | WF- Homepage Schedule Widget [FNS-64] - 6h | WF- Homepage Schedule Widget [FNS-64] - 6h |  |  | WF- Buy Tickets URL JSON [FNS-88] - 2h Fixtures & Results [FNS-87] - 4h | WF- Matchcentre [FNS-93] - 6h | WF- Matchcentre [FNS-93] - 6h | WF- Matchcentre [FNS-93] - 6h | WF- Matchcentre [FNS-93] - 6h |  |  | WF- Matchcentre [FNS-93] - 6h | Free | Free | Free | Free |  |  | Free | Free | Free | Free | Free |  |  | Free | Free | Free | Free | Holiday |  |  | Matchcentre | Matchcentre | Matchcentre | Matchcentre | Matchcentre |  |  | Matchcentre | Player Profile | Player Profile | Player Profile |  |  |  | Holiday | Free | Free | Free | Free |  |  | Free | Free | Free | Free | Free
Mala | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | Leave |  |  | Leave | SO- Terms and Conditions [FNS-29] — 4h Privacy Policy [FNS-28] — 4h | SO- Thank you [FNS-31] — 4h 404 [FNS-30] — 4h | SO- Partnership Framework [FNS-32] — 4h Where to Watch [FNS-24] — 4h | Holiday |  |  | SO- Womens t20 exhibition [FNS-25] — 4h SO- Wallpapers [FNS-23] — 4h | PVL- Player registration embed - 1h HP Static Banner - 0.5h Team strip - 2h 404 - 0.5h | PVL- T&C page - 4h About us - 3h | PVL- Hall of fame - 6h | PVL- Testing |  |  | Buy Tickets banner -0.5 Islander Banner -0.5 Esports -4 | Social Hub - 6 | Esports Player Profile -4 Terms & Conditions -2 Ticket T&C -2 | Community -2 Safeguarding -4 Privacy Policy -2 | Cookie Policy -2 Error Page -4 |  |  | Holiday | HP Squad | HP Squad + Squad page | Squad page | Showcase |  |  | MCFC Fixses | MCFC Fixses | Free | Free | Free
Mayur | NA | NA | NA | NA | NA |  |  | WF- Standing UI development [FNS-92] - 3h Standings API integration [FNS-91] - 3h Homepage Standings widget [FNS-65] - 2h | WF- Standing UI development [FNS-92] - 3h Standings API integration [FNS-91] - 3h Homepage Standings widget [FNS-65] - 2h | WF- Stats UI [FNS-90] - 4h Stats API integration [FNS-89] - 4h | WF- Stats UI [FNS-90] - 4h Stats API integration [FNS-89] - 4h | NA |  |  | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | Holiday |  |  | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA |  |  | Holiday | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA
Shubham | WF- Homepage Showcase Carousel [FNS-62] - 4h Homepage News & Videos [FNS-66] - 4h | WF- Homepage Photos [FNS-67] - 3h Homepage Squad [FNS-68] - 4h | WF- Homepage Shop Widget [FNS-69] - 2h Homepage Newsletter Widget [FNS-70] - 6h | WF- Squad Page [FNS-94] - 8h | WF- 404 [FNS-84] - 1h Custom JSON [FNS-96] - 7h |  |  | WF- Custom JSON [FNS-96] - 2h Player Profile [FNS-95] - 6h | WF- Player Profile [FNS-95] - 10h | Free | Free | Free |  |  | Free | Free | Free | Free | Free |  |  | Free | Free | Free | Free | Free |  |  | NA | All Fixture | All Fixture | All Fixture | Holiday |  |  | Both Standings | Both Standings | All Fixture | Tracker | Tracker |  |  | login TBD | [6 empty] | Holiday | Free | Free | Free | Free |  |  | Free | Free | Free | Free | Free
Siddharth N | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | Leave |  |  | SO- Registration form (popup) [FNS-33] — 4h — [FNS-34] — 4h | SO- Contact Us [FNS-35] — 4h — [FNS-36] — 4h | SO- Boundary Builder page + form [FNS-168] — 8h | SO- Unit testing fixses of all form -8h | Holiday |  |  | PVL- Header & Footer - 8h | PVL- Standings - 6h | PVL- Squad - 8h | PVL- Squad - 4h External links - 1 ticket maybe | PVL- Buffer Due to New Module |  |  | PVL Fixses | PVL Fixses | PVL Fixses | PVL- GO Live | Aapla 12th Man Poll Goal of the Month |  |  | Holiday | Aapla 12th Man Banner - 6 | Aapla 12th Man Banner - 2 New Crest New Crest Contest Terms and Conditions | Homepage Emailer - 5 Islander of the month | Goal of the season slander of the match |  |  | Save of the Month Save of the Season | Form Fixses | Form Fixses | Free | Free
Supriya | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA |  |  | SO- Videos - Listing [FNS-20] — 4h Photos - Listing [FNS-18] — 4h | SO- News - Listing [FNS-16] — 8h | SO- Photos - Listing [FNS-18] — 2h Photos - Detail [FNS-19] — 6h | SO- News - Detail [FNS-17] — 4h Fixses - 4h | Leave |  |  | SO- Videos - Detail [FNS-21] — 5h Showcase -3h | SO- Matchcentre [FNS-43] — 8h | SO- Matchcentre [FNS-43] — 8h | SO- Matchcentre [FNS-43] — 8h | Holiday |  |  | PVL- Homepage listings - 5h | PVL- All listing pages - 8h | PVL- All Detail pages - 8h | PVL- All Detail pages - 4h HP Showcase - 2h | PVL- Buffer Due to FIH |  |  | NA | NA | NA | NA | NA |  |  | Holiday | NA | NA | NA | NA
WF
SO
PVL
MCFC